## Progress & Estimate
Jigyaasaa Smart Hybrid LMS · Progress, Hours & Estimate
Hours = 8 hrs/day, Mon–Fri. Excludes Smart Classroom & Container
Time already spent |  |  | 208 hrs (26 working days)
Overall progress |  |  | ~55–60% complete
Estimated time to finish |  |  | 3–4 weeks
PRD | Module / Area | Status | Done | Hrs | What's Done | What's Left
— | Foundation & Setup | Base | — | 28 | Project scaffold, user/role model, DB models (all apps), R2 storage, seed data, test infra. | —
3.1 | User Auth & Access | In progress | 75% | 16 | Email + OTP login, JWT, password reset, roles, login logs. | Social / SSO login, device recognition.
3.2 | Course Management | Done | 90% | 24 | Courses, modules, lessons, batches, enroll, progress, reviews. | Small polish (prerequisites, discount tags).
3.3 | Paid Market Training | In progress | 50% | 8 | Trainer pricing, GST, coupons, checkout. | Revenue share, EMI, pay-per-session, referrals.
3.4 | Platform Access Pricing | In progress | 60% | 6 | Monthly / quarterly / annual plans, subscription activate. | Lock library / courses behind an active plan.
3.5 | Live Training (Google Meet) | In progress | 70% | 14 | Schedule, register + waitlist, join link, doubts, attendance. | Google Meet auto-link + calendar + reminders.
3.6 | Individual & Group Classes | In progress | 65% | 8 | 1:1 slots, booking, group sessions. | Pay-per-hour, calendar sync, invite enrollment.
3.10 | Free Online Library | Done | 85% | 12 | Search, filters, bookmarks, downloads (S3 / R2). | Premium content gating, trainer filter.
3.11 | Recording & Storage | In progress | 60% | 12 | Recordings / chapters / transcripts API + R2 storage (built). | Turn it on, pull Meet recordings, AI transcript.
3.12 | Common LMS Features | Done | 85% | 40 | Progress, quizzes (auto-grade), assignments, certificates, forum, notifications. | Coding-test grading, real Email / SMS / WhatsApp / push, PDF certs.
3.13 | Payment Module | Started | 45% | 12 | Checkout, coupons, GST invoice (MOCK gateway). | Real Razorpay / UPI + webhooks, refunds.
3.14 | Reports & Analytics | Started | 10% | 4 | Data model + seed only. | Admin + trainer dashboards (users, revenue, attendance…).
3.15 | AI Advanced Features | Not started | 0% | 0 | Not started. | Course recommendations + AI classroom (summary, heatmap).
4 | Security & Scale (NFR) | Started | 40% | 6 | Role permissions, JWT, private storage, CORS. | Load test, GDPR, multi-tenant hardening.
— | Testing & Documentation | Base | — | 18 | 74 automated tests, API reference, Swagger docs, reports. | —
OVERALL |  |  | 57% | 208 | Spent 208 hrs · remaining fits in 3–4 weeks.