## Time Spent
Jigyaasaa Smart Hybrid LMS · Time Spent by Module
Basis: 8 hrs/day · Mon–Fri (Sat & Sun excluded) · elapsed 1 month 7 days ≈ 26 working days ≈ 208 hours.
Module / Work area | Hours | Days (8h) | What was delivered
Foundation & Setup | 28 | 3.5 | Project scaffold, custom user/role model, DB models for all apps, Cloudflare R2 storage, seed data, test infra.
§3.1 User Auth & Access | 16 | 2 | Email + JWT login, refresh, logout, /me, roles, OTP login, password reset, login logs.
§3.2 Course Management | 24 | 3 | Courses, modules, lessons, resources, batches, enroll, curriculum, progress, reviews.
§3.10 Free Online Library | 12 | 1.5 | Resource CRUD, search & filters, bookmarks, popularity, S3/R2 downloads.
§3.5 Live Training | 14 | 1.75 | Sessions, register + waitlist, join link, attendance, raise-doubt.
§3.6 Individual & Group | 8 | 1 | 1:1 availability + booking, group sessions.
§3.12 Common LMS Features | 40 | 5 | Learning progress, quizzes (auto-grade), assignments, certificates, discussion forum, notifications + gamification.
§3.11 Recording & Storage | 12 | 1.5 | Recordings/chapters/transcripts API, per-user views, R2 storage (built, parked).
§3.3 Paid Market Training | 8 | 1 | Course pricing, GST, coupons, checkout scaffolding.
§3.4 Platform Access Pricing | 6 | 0.75 | Plans (monthly/quarterly/annual), subscription activation.
§3.13 Payment Module | 12 | 1.5 | Checkout, orders, invoices, GST, coupons (mock gateway).
§3.14 Reports & Analytics | 4 | 0.5 | Analytics data model + seed.
§4 Security & Scale (NFR) | 6 | 0.75 | Role permissions, JWT hardening, private storage, CORS.
Testing & Documentation | 18 | 2.25 | 74 automated tests, API reference, Swagger docs, estimates & reports.
TOTAL | 208 | 26