## Timeline
Jigyaasaa Smart Hybrid LMS — Project Timeline
High-level status & time to finish. Excludes Smart Classroom (§3.7/3.8); live classes use Google Meet.
Key figures
Time already spent | 1 month 10 days
Overall progress | ~55–60% complete
Estimated time to finish | 3–4 weeks
Where the build stands
Done | Most of the core platform is working end-to-end: accounts & login, course catalog & enrollment, learning progress & certificates, the free library, live classes (via Google Meet), quizzes & assignments, discussions, notifications, and checkout with GST invoices. File storage runs on Cloudflare R2.
Remaining | What's left is mainly integrations and reporting: connecting a real payment gateway (Razorpay/UPI) with refunds, sending notifications over email/SMS/WhatsApp/push, admin & trainer analytics dashboards, and the AI helper features. Final security & scale hardening rounds it off.
Note: ~3–4 weeks is backend/API effort for a single developer. Frontend, testing and deployment run alongside. Priority order: payment gateway → notification delivery → analytics.